## Cover Page
Navajo Townsite Community Development Corporation

## Goal 1-Customer Services
CUSTOMER SERVICE
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC must be committed to and visibly support Tenant Eduation in order to be successful. They must provide tenant education to ensure we communicate the importance of Affordable Housing, Financial Management, Health and Wellness | 1.1 Tenant Education will be held once a month for Public Rental and Homeowners | RI/OM | [5 empty] | Public Rental; 2 X a year Homeowner; 1 X a year will do education Individually
| 1.2 Provide survey to families on what they want to see | RI/OM | [5 empty] | What type of survey?
| 1.3 Provide education on the Navajo Nation Regulation regarding Animals | RI/OM | [5 empty] | will do education individually.
| 1.4 Schedule annual beautification for NTCDC families | Maintenance | [5 empty] | Yard beautification?
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC is committed to and visibly support work quality for internal/external customers. | 1.1 Ensure policies & procedures are current to address demands of current operations | Executive Director/Associate Director
| 1.2 Develop tracking of work orders that establish accountablity (cost estimating, labor and materials) | Associate Director | [5 empty] | In progress
| 1.3 Meet 100% of annual certification for homeowners and public rental families | Associate Director/RI/OM | [5 empty] | it's been done
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC must maintain professional image of NTCDC branding. | 1.1 Install signage of NTCDC services
1.2 Ensure 100% of NTCDS branding is on all correspondences.
1.3 Partner with local community to engage, and promote housing iniatives
1.4 Customer Service satisfaction 100%

## Goal 2-Productivity
Productivity
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC must be committed to and visibly support Management in order to be successful. The NTCDC has three (3) active policies, and a Plan of Operations that need to be updated to meet the current operation demands. | 1.1 Revision to the Finance policy, Housing policy (Homeownership & Public Rental), and Personnel Policy. Revisit the current Insurance Policy to ensure coverage is adequate to meet the needs/demands of the operations | Executive Director | 25% |  |  |  | The Personnel Policies and Financial Policies are revised and awaiting approval by the BOD and shared with the BOD on January 16, 2021.
| 1.2 Initate revision of the Plan of Operations/By Laws in collaberation with the Board of Directors | Executive Director and BOD | 50% |  |  |  |  | The Plan of Operations can not be located and will need to be recreated.
| 1.3 Initate revision of Housing Policy to plan for Administrative costs/fees | Executive Director & BOD
| 1.4 Initate revision of Personnel Policies and Procedures | Executive Director & BOD | 75% |  |  |  |  | The PPM have been revised and submitted to the BOD. The BOD will review and make comments, revisions, and a decision to approve.
| 1.5 Initate study to adopt building codes as part of the operation | Executive Director Associate Director
| 1.6 Revise Insurance Policy to ensure coverage is adequtate to meet the needs/demands of the operations | Executive Director | [5 empty] | Develop Insurance Policy?
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC is committed to and visibly support Management in order to be successful. The NTCDC will formally adopt resolution to obtain the Master Lease for NTCDC Public rental | 1.1 NTCDC will obtain all necessary document to obtain Master Lease for its Public Rental locate on Lone Pine | Executive Director | 0%
| 1.2 NTCDC will work with necessary professional to obtain inventory of all asbesto structures. | Associate Director
| 1.3 The NTCDC will study the feasiblity of obtain veteran housing | Executive Director
| 1.4 NTCDC will work with necessary professional to plan, develop andcreate drainage control for housing entity. | Executive Director/Associate Director
| 1.5 NTCDC will work with plan, development to create other housing options for our professional | Executive Director | [5 empty] | Essential families?
| 1.6 NTCDC will plan and development to create street lighting for our housing | Executive Director | [5 empty] | Solar lighting? Who will be paying for this?

## Goal 3- Financial Management
Financial Management
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC is committed to and visibly support Management in order to be successful. The NTCDC has employees with define roles and responsiblities. Establish channels for communication between management, employees, customers, and external officials. Ensure employees have developed minimal skills, training, and experience to do the work. | 1.1 Revision to the Finance policy, Housing policy (Homeownership & Public Rental), and Personnel Policy. Revisit the current Insurance Policy to ensure coverage is adequate to meet the needs/demands of the operations | Executive Director and BOD
| 1.2 Initate revision of the Plan of Operations/By Laws in collaberation with the Board of Directors | Executive Director and BOD
| 1.3 Initate revision of Housing Policy to plan for Administrative costs/fees | Executive Director and BOD
| 1.4 Initate study to adopt building codes as part of the operation | Executive Director Associate Director
| 1.5 Initate training for management, employees, and community stake holders | Executive Director and RI/OM
| 1.6 Initate organizational relignment to meet the demands of operations | Executive Director and Associate Director
| 1.7 Research and establish health benefits for permanent staff | Executive Director | 25% |  |  |  | Researched insurance plans, working to find plans that may be feasible in cost and coverage for NTCDC | Coverage will hopefully include medical, dental and vision
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. NTCDC is committed to and visibly support Management in order to be successful. | 1.1 Take initial steps to ensure NTCDS is in compliance to maintain its 501©3 status. | Executive Director/Bookkeeper | 100% |  |  |  | 990's are complete and submitted as of 12/31/2020 | These are due by 2/15/2021
| 1.2 Ensure financial audits are complete as required | Executive Director/Bookkeeper
| 1.3 Develop and initate inventory of all assets | Executive Director/Bookkeeper
| 1.4 Create public/private leverageing opportunites by seeking out new grant | Executive Director/BOD

## Goal 4 - Community Relations
Community Relations
Objective | Deliverables | Responsible | Percentage/Time Frame |  |  |  | Results/Metrics | Results/Notes/Comments
|  | person | 1st | 2nd | 3rd | 4th
1. The NTCDC will be successful in building partnership, relationship with external entities. | 1.1 Establish working relations with external entities | Executive Director | 25% |  |  |  |  | NTCDC is actively participating in a local task group that was awarded a small environmental justice grant to continue with assessments and remediation of the former NFPI site, the contaminant hazards and health effects to the community as a whole
| 1.2 Participate in local community meetings, activities | Executive DirectorAssociate Director | 25% |  |  |  |  | NTCDC will continue to participate in meetings regarding street improvements with the Red Lake Chapter and Navajo DOT
| 1.3 Partner with other organization to plan, develop infrastructure suitable for our housing | Executive Director BOD Associate Director | 0%

## Topic Discussion
Navajo Townsite Community Development Corporation FY2109 Strategic Plan
| Description | Category | Timeline
|  |  | 1 YR | 3rd YR | 5th YR
A. | Customer Services |  | √
Animal Control
| Litter/Trash |  | √
| Streetligting |  | √ | √ | √
| Tenant Relations |  | √
| Tenant Incentives |  | √
| Trash pick up services |  | √
| Workorders |  | √
| Beautification |  | √ | √ | √
B. | Productivity
Finance
Housing (Homeowner/Public Rental)
Maintenance
Personnel
Insurance (Homeownership/Public Rental/vehicle/General Liability/Public Officials
Leases for CDC Public Rental
Drainage control
Veterans Housing
Condos/Duplexes/Studios
Inventory of Asbesto
Health Benefits
C.
Training
Recuritment (Security, PT Worker)
Organizational Relignment
Financial Audit (Organization/NHA)
Materials Inventory
Search for new grant (street lighting, modernization, transfer station, beautification)
15 Homeownership (will end in 8 years)
G. | Community Relations
Bringing in business opportunity
Business stability (Post Office, Supermarket)
Partnering with other organization (NavajoNation, Schools, County, State, Federal)
Utility Upgrade
Transfer Station